DOCUMENT #4 FEATURE BREAKDOWN DOCUMENT Har Feature → Small Tasks → AI builds step-by-step

Krishna Academy Upleta

Online Learning Platform — Web + Android App

| Document | Version | Date | Features Covered | Total Tasks |
| --- | --- | --- | --- | --- |
| Feature Breakdown Doc #4 | v1.0 | April 2026 | 10 Core Features | 120+ atomic tasks |

Golden Rule Har badi feature ko chote atomic tasks mein todo karo. Ek task = ek AI prompt = ek commit. Yeh document AI ko exactly batata hai: kya build karna hai, kis layer pe, kitne time mein, aur kya test karna hai.

Prepared by: Tushar  |  krishnaacademyupleta.vercel.app

# How to Read This Document

For AI Tools (Cursor / v0 / Claude / ChatGPT) Har task ki 'Detail / AI Prompt Hint' column ko AI ko seedha paste karo. Ek task = ek conversation. Status 'To-Do' wale tasks ko pehle lo. P0 pehle, P1 baad mein.

| Column | Meaning | Values |
| --- | --- | --- |
| # | Task ID — unique reference | F1.1, F1.2, F2.1 ... |
| Layer | Which part of codebase | Frontend ¦ Backend ¦ Database ¦ Full Stack ¦ App ¦ Test |
| Pri | Priority level | P0=Launch blocker ¦ P1=Phase2 ¦ P2=Phase3 ¦ P3=Nice-to-have |
| Time | Estimated dev time | 30m / 1h / 2h / 4h / 1d / 2d |
| Status | Current state | ✅ Done ¦ 🔄 In Progress ¦ ⬜ To-Do ¦ 🧪 Test ¦ 🚫 Blocked |
| Detail | AI prompt hint | What to tell AI to build this exact task |

| Feature # | Feature Name | Total Tasks | Est. Total Time | Priority |
| --- | --- | --- | --- | --- |
| Feature 1 | Authentication & OTP | 12 tasks | ~14 hours | P0 — Launch blocker |
| Feature 2 | Course Catalog & Enrollment | 14 tasks | ~18 hours | P0 — Launch blocker |
| Feature 3 | Video Player (Recorded) | 13 tasks | ~16 hours | P0 — Launch blocker |
| Feature 4 | Live Classes (Agora) | 14 tasks | ~20 hours | P0 — Launch blocker |
| Feature 5 | Homework System | 12 tasks | ~14 hours | P0 — Launch blocker |
| Feature 6 | Attendance Tracking | 10 tasks | ~10 hours | P0 — Launch blocker |
| Feature 7 | Notes / PDF System | 9 tasks | ~8 hours | P0 — Launch blocker |
| Feature 8 | Practice Tests & Quizzes | 14 tasks | ~18 hours | P1 — Phase 2 |
| Feature 9 | Payments & Subscriptions | 13 tasks | ~16 hours | P0 — Launch blocker |
| Feature 10 | Admin & Teacher Dashboards | 12 tasks | ~14 hours | P1 — Phase 2 |

FEATURE 1 Authentication & OTP System Mobile OTP login — no passwords. Supabase Auth + MSG91 SMS + JWT tokens. Role-based: Student / Teacher / Admin.

| # | Task / Sub-task | Layer | Pri | Time | Status | Detail / AI Prompt Hint |
| --- | --- | --- | --- | --- | --- | --- |
| F1.1 | Supabase project setup + DB connection | 🗄 Database | 🔴 P0 | 1h | ⬜ To-Do | Create Supabase project. Add DATABASE_URL to .env. Run: npx prisma init. Configure prisma schema for PostgreSQL. |
| F1.2 | Prisma User model + migration | 🗄 Database | 🔴 P0 | 30m | ⬜ To-Do | Create User model with fields: id, phone, name, class_level, stream, goal, role(enum), plan(enum), created_at. Run npx prisma migrate dev. |
| F1.3 | MSG91 OTP send API route | ⚙ Backend | 🔴 P0 | 1h | ⬜ To-Do | POST /api/v1/auth/otp/send. Validate phone (10 digits, Indian). Generate 6-digit OTP. Store hash(OTP)+expiry in Upstash Redis. Call MSG91 REST API to send SMS. |
| F1.4 | OTP hash storage in Redis | ⚙ Backend | 🔴 P0 | 30m | ⬜ To-Do | Use @upstash/redis. Key: otp:{phone}. Value: { hash: bcrypt(otp), expires: Date.now()+5min }. Set TTL=5min. Delete key after successful verify. |
| F1.5 | OTP verify + JWT issue API route | ⚙ Backend | 🔴 P0 | 2h | ⬜ To-Do | POST /api/v1/auth/otp/verify. Compare hash(submitted) with Redis. On match: check if user exists → create if new. Issue JWT(15min, payload:{userId,role,plan}) + refresh token(30d, HttpOnly cookie). |
| F1.6 | JWT middleware for protected routes | ⚙ Backend | 🔴 P0 | 1h | ⬜ To-Do | Create middleware.ts in Next.js root. Extract Bearer token from Authorization header. Verify JWT with jose library. Inject x-user-id, x-user-role, x-user-plan into request headers. |
| F1.7 | Refresh token rotation | ⚙ Backend | 🔴 P0 | 1h | ⬜ To-Do | POST /api/v1/auth/refresh. Read HttpOnly cookie. Validate refresh token from DB. Issue new access token + rotate refresh token (delete old, store new hashed in DB). |
| F1.8 | OTP login UI — phone input screen | 🖥 Frontend | 🔴 P0 | 2h | ⬜ To-Do | Build /auth page. Phone input with +91 flag. Validate 10 digits. Call POST /api/v1/auth/otp/send. Show loading state. On success navigate to OTP verify screen. |
| F1.9 | OTP verify UI — 6-box input + timer | 🖥 Frontend | 🔴 P0 | 2h | ⬜ To-Do | 6 individual input boxes. Auto-advance on digit entry. 5-min countdown timer. Resend button (enabled after 30s). Auto-submit when 6th digit entered. Show error on wrong OTP. |
| F1.10 | Onboarding flow — 4-step wizard | 🖥 Frontend | 🔴 P0 | 2h | ⬜ To-Do | 4 steps: (1)Name (2)Class/Stream (3)Goal selection (4)Subject selection. Progress bar at top. Skip allowed. Save to PUT /api/v1/auth/profile. On complete → redirect to /dashboard. |
| F1.11 | Zustand authStore + token management | 🖥 Frontend | 🔴 P0 | 1h | ⬜ To-Do | Zustand store: { user, accessToken, plan, setUser, setToken, logout }. Access token in memory ONLY — never localStorage. Auto-refresh via Axios interceptor when 401 received. |
| F1.12 | Auth flow E2E test | 🧪 Test | 🔴 P0 | 1h | ⬜ To-Do | Test: send OTP → verify OTP → check JWT issued → check refresh cookie set → hit protected route → check 401 without token → check 403 wrong role → test token refresh flow. |

FEATURE 2 Course Catalog & Enrollment Browse courses, view details, free preview video, enroll/pay. Filter by class/subject/exam type. Course cards with ratings.

| # | Task / Sub-task | Layer | Pri | Time | Status | Detail / AI Prompt Hint |
| --- | --- | --- | --- | --- | --- | --- |
| F2.1 | Prisma Course + Chapter + Video models | 🗄 Database | 🔴 P0 | 1h | ⬜ To-Do | Create Course(id,teacher_id,title,slug,subject,category,is_free,price,thumbnail_url,is_published), Chapter(course_id,title,order_index), Video(chapter_id,title,r2_key,hls_key,duration_sec,is_free). Run migration. |
| F2.2 | Enrollment + VideoProgress models | 🗄 Database | 🔴 P0 | 30m | ⬜ To-Do | Enrollment(student_id,course_id,enrolled_at,progress_percent,last_watched_video_id). VideoProgress composite PK(user_id,video_id) with watched_sec+is_completed. Run migration. |
| F2.3 | GET /api/v1/courses — listing with filters | ⚙ Backend | 🔴 P0 | 2h | ⬜ To-Do | Query params: ?class=11&subject=physics&is_free=true&exam=jee&sort=popular&page=1. Prisma query with where filters + orderBy (enrollments count for popular). Return paginated 12 courses per page with cursor pagination. |
| F2.4 | GET /api/v1/courses/:slug — course detail | ⚙ Backend | 🔴 P0 | 1h | ⬜ To-Do | Return full course: chapters with videos list (duration, is_free flag, locked status based on user plan). Include teacher profile, avg rating, review count, total enrolled. First video of each chapter always unlocked. |
| F2.5 | POST /api/v1/courses/:id/enroll | ⚙ Backend | 🔴 P0 | 1h | ⬜ To-Do | Check if already enrolled → return 409. Free course: create Enrollment record directly. Paid course: verify Subscription is active → then create Enrollment. Return { enrolled: true }. |
| F2.6 | Course listing page UI | 🖥 Frontend | 🔴 P0 | 3h | ⬜ To-Do | Build /courses page. Filter sidebar: Class (9-12), Subject, Exam type, Price (free/paid), Language. Sort dropdown. Course cards grid (4 col desktop, 2 tablet, 1 mobile). Infinite scroll or pagination. Loading skeleton cards. |
| F2.7 | Course card component | 🖥 Frontend | 🔴 P0 | 1h | ⬜ To-Do | CourseCard component: thumbnail, title, teacher name+avatar, star rating, student count, language badge (Hinglish), price tag (FREE / Rs.149). Hover: slight shadow lift. Click → course detail page. |
| F2.8 | Course detail page UI | 🖥 Frontend | 🔴 P0 | 3h | ⬜ To-Do | Build /courses/[slug] page. Sections: hero (thumbnail+title+CTA), curriculum accordion (chapters+videos with lock icons), about teacher, what you'll learn, student reviews, sticky sidebar with price+enroll button. |
| F2.9 | Curriculum accordion component | 🖥 Frontend | 🔴 P0 | 1h | ⬜ To-Do | Expandable chapter accordion. Each chapter shows video list. Video row: play icon, title, duration, FREE/LOCKED badge. Click free video → open player. Click locked → show upgrade prompt if not subscribed. |
| F2.10 | Enroll button logic + plan gate | 🖥 Frontend | 🔴 P0 | 1h | ⬜ To-Do | Enroll button states: Not logged in → Show login modal. Free course → POST enroll → show success. Paid course + no sub → open paywall modal. Paid course + active sub → POST enroll directly. |
| F2.11 | Teacher creates course — Course Builder | 🖥 Frontend | 🔴 P0 | 3h | ⬜ To-Do | Build /teacher/courses/create. Multi-step: (1)Basic info: title, subject, class, exam type, thumbnail upload (2)Curriculum builder: add chapters, reorder with drag-drop (3)Pricing: free/paid toggle + price input (4)Publish toggle. |
| F2.12 | POST /api/v1/courses — teacher creates course | ⚙ Backend | 🔴 P0 | 1h | ⬜ To-Do | Validate role=TEACHER. Auto-generate slug from title (slugify). Create Course record with is_published=false. Return course_id for teacher to add chapters+videos next. |
| F2.13 | Next.js ISR for course listing | 🖥 Frontend | 🟡 P1 | 1h | ⬜ To-Do | Add revalidate=3600 to course listing page (ISR). Course detail pages: generateStaticParams for all published course slugs. revalidate=1800. This makes pages load instantly from CDN. |
| F2.14 | Course catalog E2E test | 🧪 Test | 🔴 P0 | 1h | ⬜ To-Do | Test: list courses with filter → check pagination → open course detail → check curriculum → enroll free course → check enrollment created → try to enroll again → check 409 → test locked video gate. |

FEATURE 3 Video Player (Recorded Courses) Custom HLS player — NOT YouTube. Resume, speed control, progress tracking, offline download (app), personal notes panel.

| # | Task / Sub-task | Layer | Pri | Time | Status | Detail / AI Prompt Hint |
| --- | --- | --- | --- | --- | --- | --- |
| F3.1 | Cloudflare R2 bucket setup + SDK config | ⚙ Backend | 🔴 P0 | 1h | ⬜ To-Do | Create R2 bucket 'krishna-academy'. Configure @aws-sdk/client-s3 with R2 endpoint (account_id.r2.cloudflarestorage.com). Add env vars: R2_ACCOUNT_ID, R2_ACCESS_KEY_ID, R2_SECRET_ACCESS_KEY, R2_BUCKET_NAME. |
| F3.2 | Video upload — presigned URL flow | ⚙ Backend | 🔴 P0 | 2h | ⬜ To-Do | POST /api/v1/courses/:id/videos — validate TEACHER role. Create Video DB record (status:UPLOADING). Call R2 createPresignedPost({key: courses/{courseId}/{uuid}.mp4, expiry:1hr}). Return {uploadUrl, videoId} to frontend. |
| F3.3 | Video upload UI — teacher uploads MP4 | 🖥 Frontend | 🔴 P0 | 2h | ⬜ To-Do | File input accepts MP4/MOV max 2GB. Show progress bar (track XMLHttpRequest upload progress to presigned URL). On upload complete: call POST /api/v1/videos/:id/process. Show 'Processing...' state with spinner. |
| F3.4 | HLS transcoding via Cloudflare Worker | ⚙ Backend | 🔴 P0 | 3h | ⬜ To-Do | Create Cloudflare Worker triggered by R2 upload event. Worker: fetches raw MP4, uses ffmpeg WASM to create 360p.m3u8, 480p.m3u8, 720p.m3u8, master.m3u8. Uploads HLS segments back to R2. Updates Video DB record: hls_key, status:READY. |
| F3.5 | GET /api/v1/videos/:id/stream-url | ⚙ Backend | 🔴 P0 | 1h | ⬜ To-Do | Check auth + plan gate (FREE: only videos with is_free=true). Generate R2 signed URL for hls_key with expiry=15min. Return {streamUrl}. Frontend HLS player loads this URL directly from Cloudflare CDN. |
| F3.6 | Custom HLS video player component (web) | 🖥 Frontend | 🔴 P0 | 3h | ⬜ To-Do | Build VideoPlayer component using HLS.js + HTML5 video. Features: custom controls bar (play/pause, progress scrubber, volume, fullscreen), speed selector (0.5/0.75/1/1.25/1.5/2x), quality selector (360p/480p/720p/Auto), loading buffer indicator. |
| F3.7 | Resume playback — save + restore position | 🖥+⚙ Full Stack | 🔴 P0 | 1h | ⬜ To-Do | Frontend: on video 'timeupdate' event every 10s → PUT /api/v1/videos/:id/progress {watched_sec}. On video load: GET progress → set video.currentTime = watched_sec. Mark complete when watched_sec > duration*0.8. |
| F3.8 | PUT /api/v1/videos/:id/progress | ⚙ Backend | 🔴 P0 | 30m | ⬜ To-Do | Upsert VideoProgress record. If watched_sec > video.duration*0.8 → set is_completed=true. Recalculate enrollment.progress_percent = (completed videos / total videos * 100). |
| F3.9 | Curriculum sidebar + chapter accordion | 🖥 Frontend | 🔴 P0 | 2h | ⬜ To-Do | Right sidebar (desktop) / bottom sheet (mobile) shows all chapters + videos. Current video highlighted in blue. Completed videos show green checkmark. Locked videos show lock icon. Click video → fetch stream URL → load in player. |
| F3.10 | Personal notes panel (timestamped) | 🖥+⚙ Full Stack | 🟡 P1 | 2h | ⬜ To-Do | Notes panel alongside video. Click 'Add Note' → captures current timestamp → text input opens. Notes stored in DB: {user_id, video_id, timestamp_sec, note_text}. Notes list shows all notes for this video sorted by timestamp. |
| F3.11 | Offline download (Android app only) | 📱 App | 🟡 P1 | 3h | ⬜ To-Do | Use react-native-fs. Download HLS segments + m3u8 to encrypted app sandbox (AES-256). Show download progress. Max 20 videos. Offline indicator in curriculum list. ExoPlayer reads local encrypted HLS for playback. |
| F3.12 | Picture-in-Picture mode (Android) | 📱 App | 🟢 P2 | 1h | ⬜ To-Do | Enable android:supportsPictureInPicture=true in AndroidManifest. In react-native-video: onUserLeaveHint → enterPictureInPicture(). Show minimal controls in PiP. Resume full screen on tap. |
| F3.13 | Video player E2E test | 🧪 Test | 🔴 P0 | 1h | ⬜ To-Do | Test: get stream URL (auth + plan gate) → load HLS → check quality levels loaded → save progress at 10s → reload page → check resume at 10s → watch 80% → check is_completed=true → check enrollment progress updated. |

FEATURE 4 Live Classes (Agora RTC) Teacher broadcasts live. Students watch + chat. Auto attendance. Auto recording saved to R2. Notifications 30min before.

| # | Task / Sub-task | Layer | Pri | Time | Status | Detail / AI Prompt Hint |
| --- | --- | --- | --- | --- | --- | --- |
| F4.1 | Agora.io account setup + SDK install | ⚙ Backend | 🔴 P0 | 1h | ⬜ To-Do | Create Agora account. Get App ID + App Certificate. Install: npm install agora-access-token (server token gen). Install on web: agora-rtc-sdk-ng. Add env vars: AGORA_APP_ID, AGORA_APP_CERTIFICATE. |
| F4.2 | Prisma LiveClass + LiveAttendance models | 🗄 Database | 🔴 P0 | 30m | ⬜ To-Do | LiveClass(teacher_id,subject,title,batch_ids[],scheduled_at,agora_channel,recording_url,status enum,max_students). LiveAttendance(live_class_id,student_id,joined_at,left_at,duration_min,status enum). Run migration. |
| F4.3 | POST /api/v1/live — teacher schedules class | ⚙ Backend | 🔴 P0 | 1h | ⬜ To-Do | Validate role=TEACHER. Generate agora_channel = 'ka_' + cuid(). Create LiveClass DB record. Trigger FCM push notification to all students in batch_ids (30min reminder scheduled via cron or Vercel Cron). Return live class object. |
| F4.4 | GET /api/v1/live/:id/teacher-token | ⚙ Backend | 🔴 P0 | 30m | ⬜ To-Do | Validate role=TEACHER + is class teacher. Generate Agora token: RtcTokenBuilder.buildTokenWithUid(appId, appCertificate, channelName, uid=teacher_id, role=PUBLISHER, expireTs=now+4hrs). Return token + channel name. |
| F4.5 | GET /api/v1/live/:id/token — student joins | ⚙ Backend | 🔴 P0 | 1h | ⬜ To-Do | Check FREE plan limit: count LiveAttendance this month for student. If >=3 and plan=FREE → return 403 UPGRADE_REQUIRED. Generate Agora SUBSCRIBER token. Create LiveAttendance record {joined_at: now()}. Return token + channel. |
| F4.6 | Live class room UI — student view | 🖥 Frontend | 🔴 P0 | 4h | ⬜ To-Do | Build /live/[classId] page. Agora SDK: join channel with token. Video stream display (teacher's video fills screen). Right panel: live chat (Supabase Realtime). Bottom bar: hand-raise button, poll button. Show live viewer count. |
| F4.7 | Teacher broadcast UI | 🖥 Frontend | 🔴 P0 | 2h | ⬜ To-Do | Teacher view: show own camera preview. Mute/unmute controls. Screen share toggle. Chat panel. Poll creator: type question + 4 options → broadcast to all students. Pin question from chat. 'End Class' button with confirm dialog. |
| F4.8 | Live chat via Supabase Realtime | 🖥+⚙ Full Stack | 🔴 P0 | 2h | ⬜ To-Do | Supabase Realtime channel: 'live_chat_{classId}'. On message send: INSERT into live_messages table → Supabase broadcasts to all subscribers. On join: subscribe to channel + fetch last 50 messages. Rate limit: 1 message per 3 seconds per user. |
| F4.9 | PUT /api/v1/live/:id/end — teacher ends class | ⚙ Backend | 🔴 P0 | 1h | ⬜ To-Do | Update LiveClass status=ENDED. Trigger Agora cloud recording stop → recording file URL returned. Upload recording to R2. Update recording_url in DB. Send FCM push to all attended students: 'Recording ready!'. Calculate and finalize attendance records. |
| F4.10 | POST /api/v1/live/:id/leave — auto attendance | ⚙ Backend | 🔴 P0 | 1h | ⬜ To-Do | Update LiveAttendance: left_at=now(), duration_min=diff(joined_at,now()). Set status: >=10min=PRESENT, 5-9min=PARTIAL, <5min=ABSENT. Also handle page close (send beacon request on window beforeunload event). |
| F4.11 | Live class listing + upcoming schedule UI | 🖥 Frontend | 🔴 P0 | 2h | ⬜ To-Do | Show upcoming classes as cards with countdown timer. LIVE NOW classes show pulsing red badge. Past classes show 'Watch Recording' button. Calendar view (weekly) in teacher portal. Student view: only classes for their enrolled batches. |
| F4.12 | 30-minute reminder — Vercel Cron job | ⚙ Backend | 🟡 P1 | 1h | ⬜ To-Do | Vercel Cron: runs every minute. Query LiveClass where scheduled_at BETWEEN (now+28min) AND (now+32min) AND status=SCHEDULED. For each: fetch student list → send FCM push + WhatsApp notification. Mark reminder_sent=true. |
| F4.13 | Polls feature — teacher creates, students answer | 🖥+⚙ Full Stack | 🟡 P1 | 2h | ⬜ To-Do | Teacher sends poll via Supabase Realtime: {type:'poll', question, options:[]}. All student UIs show poll overlay. Students click option → sends vote via Realtime. Teacher sees live vote count per option. Auto-close after 60 seconds. |
| F4.14 | Live class E2E test | 🧪 Test | 🔴 P0 | 1h | ⬜ To-Do | Test: teacher schedules class → student gets notification → student joins (free limit check) → attendance record created → chat message sent → received by another client → teacher ends class → recording URL saved → attendance finalized. |

FEATURE 5 Homework System Teacher creates → WhatsApp notification → Student uploads photo/PDF → Teacher reviews + grades + feedback. Deadline tracking.

| # | Task / Sub-task | Layer | Pri | Time | Status | Detail / AI Prompt Hint |
| --- | --- | --- | --- | --- | --- | --- |
| F5.1 | Prisma Homework + Submission models | 🗄 Database | 🔴 P0 | 30m | ⬜ To-Do | Homework(teacher_id,batch_ids[],title,description,attachment_url,deadline DateTime,max_marks Int?). Submission(homework_id,student_id,file_urls String[],submitted_at,is_late,marks Int?,feedback,graded_at). @@unique([homework_id,student_id]). Run migration. |
| F5.2 | POST /api/v1/homework — teacher creates | ⚙ Backend | 🔴 P0 | 1h | ⬜ To-Do | Validate role=TEACHER. Create Homework record. If attachment: generate R2 presigned URL for teacher to upload PDF. After create: trigger notification job → send FCM push + WhatsApp to all students in batch_ids. |
| F5.3 | GET /api/v1/homework — student's homework list | ⚙ Backend | 🔴 P0 | 1h | ⬜ To-Do | Fetch homework for student's enrolled batch_ids. Join with Submission to get student's submission status. Sort: pending (by deadline ASC) first, then submitted, then graded. Return is_late flag based on submitted_at vs deadline. |
| F5.4 | POST /api/v1/homework/:id/submit — student submits | ⚙ Backend | 🔴 P0 | 2h | ⬜ To-Do | Check deadline: if past → set is_late=true (still allow). Generate R2 presigned PUT URLs for each file (max 5, types: jpg/png/pdf, max 10MB each). Return [{fileIndex, uploadUrl, r2Key}]. Create Submission record with pending file_urls. |
| F5.5 | Confirm file upload + update submission | ⚙ Backend | 🔴 P0 | 30m | ⬜ To-Do | POST /api/v1/homework/:id/submit/confirm. Frontend calls this after all files uploaded to R2. Update Submission.file_urls = confirmed R2 keys. Set submitted_at = now(). Send notification to teacher: 'New submission received'. |
| F5.6 | Homework list UI — student view | 🖥 Frontend | 🔴 P0 | 2h | ⬜ To-Do | Build /homework page. Tabs: Pending / Submitted / Graded. Each card shows: title, subject, teacher name, deadline countdown (red if <6hr), submit button. Graded cards show marks and feedback snippet. Empty state per tab. |
| F5.7 | File upload modal — camera + file picker | 🖥+⚙ Full Stack | 🔴 P0 | 2h | ⬜ To-Do | Upload modal: two options — (1) camera capture (getUserMedia on web, expo-camera on app) (2) file picker (PDF/JPG). Show thumbnails of selected files. Upload to R2 presigned URLs with progress per file. Confirm when all done. |
| F5.8 | Teacher homework management UI | 🖥 Frontend | 🔴 P0 | 2h | ⬜ To-Do | Build /teacher/homework page. Create homework form: title, description, deadline (date+time picker), batch select (multi), max marks, optional attachment. View submissions list: student name, submitted at, is_late badge, review button. |
| F5.9 | Teacher grades submission UI | 🖥 Frontend | 🔴 P0 | 1h | ⬜ To-Do | Submission review page: show uploaded files (PDF viewer / image gallery). Marks input (0 to max_marks). Feedback text area. Save → PUT /api/v1/homework/:id/submissions/:sid. Student gets push notification on grade. |
| F5.10 | PUT /api/v1/homework/:id/submissions/:sid — grade | ⚙ Backend | 🔴 P0 | 30m | ⬜ To-Do | Validate role=TEACHER + is homework owner. Update Submission: marks, feedback, graded_at=now(). Trigger FCM push to student: 'Your {homework.title} has been graded! Score: {marks}/{max_marks}'. |
| F5.11 | Deadline reminder cron — 24hr + 2hr before | ⚙ Backend | 🟡 P1 | 1h | ⬜ To-Do | Vercel Cron runs hourly. Query homework where deadline IN (now+23hr to now+25hr) → send 24hr reminder to students who haven't submitted. Query deadline IN (now+1.5hr to now+2.5hr) → send 2hr urgent reminder. |
| F5.12 | Homework system E2E test | 🧪 Test | 🔴 P0 | 1h | ⬜ To-Do | Test: teacher creates HW → notification sent → student submits (on-time + late) → is_late flag correct → teacher grades → student notification sent → check marks visible in student UI → bulk download ZIP works. |

FEATURE 6 Attendance Tracking Auto-tracked from live class join/leave. Per-student % per subject. Low attendance WhatsApp alert. Monthly PDF report.

| # | Task / Sub-task | Layer | Pri | Time | Status | Detail / AI Prompt Hint |
| --- | --- | --- | --- | --- | --- | --- |
| F6.1 | Attendance calculation logic (utility fn) | ⚙ Backend | 🔴 P0 | 1h | ⬜ To-Do | Create lib/attendance.ts. Function: calculateAttendance(joined_at, left_at) → returns status: if duration>=10min return PRESENT, 5-9min return PARTIAL, <5min return ABSENT. Mark as LATE if joined_at > scheduled_at+15min. |
| F6.2 | GET /api/v1/attendance/me — student attendance | ⚙ Backend | 🔴 P0 | 1h | ⬜ To-Do | Fetch all LiveAttendance for student. Group by subject. Calculate: total classes held vs attended. Return: { overall_pct, by_subject: [{subject, held, attended, pct}], calendar: [{date, status}] for last 90 days }. |
| F6.3 | GET /api/v1/attendance/class/:id — teacher view | ⚙ Backend | 🔴 P0 | 1h | ⬜ To-Do | Fetch LiveAttendance for all students in this class. Return: { class_avg_pct, students: [{student_id, name, status, duration_min, joined_at}] }. Support date range filter ?from=&to=. Support CSV export. |
| F6.4 | Student attendance page UI | 🖥 Frontend | 🔴 P0 | 2h | ⬜ To-Do | Build /attendance page. Top: overall % circular badge (green >75%, orange 60-75%, red <60%). Subject breakdown table with progress bars. Calendar heatmap (90 days): green=present, orange=partial, red=absent, gray=no class. |
| F6.5 | Teacher attendance view UI | 🖥 Frontend | 🔴 P0 | 1h | ⬜ To-Do | Build /teacher/attendance. Dropdown to select class/date. Table: student name, status badge, duration, join time. Summary: present count, absent count, avg duration. Export CSV button. |
| F6.6 | Low attendance alert — auto WhatsApp | ⚙ Backend | 🟡 P1 | 1h | ⬜ To-Do | Cron runs daily. Query students where overall_attendance_pct < 75. For each: check if alert sent in last 7 days (Redis key: alert:{userId}). If not: send WhatsApp message via Meta API. Set Redis key TTL=7days. |
| F6.7 | 3-consecutive-absent alert to admin | ⚙ Backend | 🟡 P1 | 1h | ⬜ To-Do | After each live class ends: check students who were ABSENT for last 3 consecutive classes of same subject. If any: send push notification to admin: 'Riya Patel has missed 3 Physics classes in a row.' |
| F6.8 | Monthly attendance report PDF | ⚙ Backend | 🟡 P1 | 2h | ⬜ To-Do | GET /api/v1/attendance/report?month=2026-04 (admin only). Use @react-pdf/renderer to generate PDF report: header, per-student table, subject breakdown, summary stats. Return PDF buffer. Admin can download or send via WhatsApp. |
| F6.9 | Attendance badge on student dashboard | 🖥 Frontend | 🔴 P0 | 30m | ⬜ To-Do | Dashboard widget: circular progress badge showing overall attendance %. Color coded. Tap → navigate to /attendance full page. Show warning icon if below 75%. |
| F6.10 | Attendance tracking E2E test | 🧪 Test | 🔴 P0 | 1h | ⬜ To-Do | Test: join class at T+0 → leave at T+12min → check status=PRESENT. Join at T+0 → leave T+6min → PARTIAL. Never join → ABSENT. Check overall % calculation. Check low attendance alert threshold. Check calendar heatmap data. |

FEATURE 7 Notes & PDF System Teacher uploads PDFs per chapter. Students view online (free) or download (paid). Tagged by subject+chapter. Personal notes.

| # | Task / Sub-task | Layer | Pri | Time | Status | Detail / AI Prompt Hint |
| --- | --- | --- | --- | --- | --- | --- |
| F7.1 | Prisma Note model + migration | 🗄 Database | 🔴 P0 | 30m | ⬜ To-Do | Note(id,course_id,chapter_id?,title,pdf_r2_key,is_free,file_size_kb,page_count?,subject,class_level,uploaded_at). Also create PersonalNote(user_id,video_id,timestamp_sec,note_text,created_at). Run migration. |
| F7.2 | POST /api/v1/notes — teacher uploads note | ⚙ Backend | 🔴 P0 | 1h | ⬜ To-Do | Validate role=TEACHER. Generate R2 presigned URL for PDF upload (max 50MB). Create Note record with pdf_r2_key, is_free flag. Trigger push notification to enrolled students if is_free=false batch note. |
| F7.3 | GET /api/v1/notes — student browse notes | ⚙ Backend | 🔴 P0 | 1h | ⬜ To-Do | Query params: ?subject=physics&chapter=3&class=11&is_free=true. Return notes list with: title, subject, chapter, page_count, file_size, is_free, uploaded_at. Do NOT return pdf_r2_key — only return IDs. |
| F7.4 | GET /api/v1/notes/:id/url — get PDF access URL | ⚙ Backend | 🔴 P0 | 1h | ⬜ To-Do | For view (all users): return R2 signed URL expiry=1hr (view only, no download header). For download (paid users only): return signed URL with Content-Disposition:attachment expiry=30min. FREE users get 403 on download attempt. |
| F7.5 | Notes library page UI | 🖥 Frontend | 🔴 P0 | 2h | ⬜ To-Do | Build /notes page. Filter bar: Subject, Chapter, Class. Note cards grid: title, subject chip, page count, file size, FREE/PAID badge. Click → open inline PDF viewer. Download button: active for paid, lock icon for free with upgrade tooltip. |
| F7.6 | PDF viewer component | 🖥 Frontend | 🔴 P0 | 1h | ⬜ To-Do | Use react-pdf (pdfjs-dist). Renders PDF pages in browser without download. Page navigation (prev/next), zoom controls. Loading skeleton while PDF loads. Error state if PDF fails to load. |
| F7.7 | Notes upload UI — teacher portal | 🖥 Frontend | 🔴 P0 | 1h | ⬜ To-Do | Build notes upload section in /teacher/courses/[id]. Drag-drop or click to upload PDF. Auto-detect file size. Title input. Subject + chapter selector. Free/paid toggle. Upload progress bar. Success state shows note in list. |
| F7.8 | Personal notes panel (timestamped to video) | 🖥+⚙ Full Stack | 🟡 P1 | 2h | ⬜ To-Do | In video player: 'My Notes' tab. Click '+' → captures current video timestamp. Text area opens. On save: POST /api/v1/notes/personal {video_id, timestamp_sec, note_text}. Notes list shows all notes sorted by timestamp, click jumps to that time in video. |
| F7.9 | Notes system E2E test | 🧪 Test | 🔴 P0 | 1h | ⬜ To-Do | Test: teacher uploads PDF → R2 key saved → FREE user views (get signed URL) → FREE user tries download → 403 → PAID user downloads → success → PDF renders in viewer → personal note created with timestamp → click jumps video. |

FEATURE 8 Practice Tests & Quizzes MCQ tests with timer, negative marking, question palette. Post-test: score, accuracy, weak chapters, leaderboard.

| # | Task / Sub-task | Layer | Pri | Time | Status | Detail / AI Prompt Hint |
| --- | --- | --- | --- | --- | --- | --- |
| F8.1 | Prisma Test + Question + TestAttempt models | 🗄 Database | 🟡 P1 | 1h | ⬜ To-Do | Test(teacher_id,batch_ids[],title,type enum,subject,timer_minutes,neg_marking Float,total_marks,is_published,available_from,available_to). Question(test_id,question_text,option_a/b/c/d,correct_option,explanation,marks,order_index). TestAttempt(test_id,student_id,answers Json,score,correct,incorrect,skipped,time_taken_sec,started_at,submitted_at). @@unique([test_id,student_id]). Run migration. |
| F8.2 | POST /api/v1/tests — teacher creates test | ⚙ Backend | 🟡 P1 | 1h | ⬜ To-Do | Validate role=TEACHER. Create Test record. Accept questions array in same request → bulk create Question records. Validate: each question has exactly 4 options + correct_option in [a,b,c,d]. Return test_id. |
| F8.3 | POST /api/v1/tests/:id/start — student starts | ⚙ Backend | 🟡 P1 | 1h | ⬜ To-Do | Check FREE plan limit (2 tests/week → count attempts this week). Check if already attempted (@@unique). Check available_from/to window. Create TestAttempt {started_at:now()}. Return questions WITHOUT correct_option or explanation (hidden). |
| F8.4 | POST /api/v1/tests/:id/submit — auto score | ⚙ Backend | 🟡 P1 | 2h | ⬜ To-Do | Receive answers:{q_id:option}. For each question: compare with correct_option. Score: +marks for correct, -neg_marking for incorrect, 0 for skipped. Calculate: total_score, correct count, incorrect count, skipped count, time_taken_sec. Update TestAttempt. Return result immediately. |
| F8.5 | Score calculation + leaderboard rank | ⚙ Backend | 🟡 P1 | 1h | ⬜ To-Do | After submit: query all attempts for this test. Rank by score DESC, then time_taken_sec ASC (faster = better rank at same score). Return student's rank + total attempts count + top 10 leaderboard {rank, name, score}. |
| F8.6 | Test taking UI — question + palette | 🖥 Frontend | 🟡 P1 | 4h | ⬜ To-Do | Build /tests/[testId] page. Header: test name + countdown timer (turns red at <5min). Question area: Q number, question text, 4 option buttons (click to select, click again to deselect). Question palette: grid of Q numbers, color coded (answered/flagged/skipped/current). Bottom: Previous, Flag & Next, Next buttons. |
| F8.7 | Test timer — auto-submit on 0:00 | 🖥 Frontend | 🟡 P1 | 1h | ⬜ To-Do | useEffect countdown from timer_minutes*60. Store in Zustand testStore.timeLeft. On reach 0: auto-call submit API with current answers. Warn user 5 min before: toast notification. Persist answers in sessionStorage every 30s (browser crash protection). |
| F8.8 | Test result page — score + analysis | 🖥 Frontend | 🟡 P1 | 2h | ⬜ To-Do | Build /tests/[testId]/result page. Score card: total/max, correct/incorrect/skipped counts, time taken, percentile rank. Accuracy % gauge. Weak chapters list (subjects where accuracy <50%). Answer key: each Q with correct answer highlighted + explanation. Leaderboard top 10. |
| F8.9 | Teacher test builder UI | 🖥 Frontend | 🟡 P1 | 3h | ⬜ To-Do | Build /teacher/tests/create. Step 1: Test settings (title, type, subject, timer, negative marking toggle+value, available from/to). Step 2: Question builder — add questions one by one, each with 4 options, select correct answer, add explanation. Reorder questions. Preview test. Publish. |
| F8.10 | Weekly performance report — student | 🖥+⚙ Full Stack | 🟡 P1 | 2h | ⬜ To-Do | GET /api/v1/tests/analytics/me. Return: subject-wise accuracy % (last 30 days), weak chapters (accuracy <50%), score trend array for line chart, total tests taken, avg score. Display in /dashboard as performance widget. |
| F8.11 | Daily quiz — auto-scheduled | ⚙ Backend | 🟢 P2 | 1h | ⬜ To-Do | Cron job (daily 8am): for each active batch, pick 10 questions from question bank for today's chapter (based on course progress avg). Create Test record (type=QUIZ, available today only). Send push notification to all batch students. |
| F8.12 | Test attempt page-leave protection | 🖥 Frontend | 🟡 P1 | 30m | ⬜ To-Do | Add beforeunload event listener during active test. Show browser warning: 'Test in progress — are you sure you want to leave?' Answers are auto-saved in sessionStorage every 30s. On return to page: restore saved answers from sessionStorage. |
| F8.13 | Teacher test analytics UI | 🖥 Frontend | 🟡 P1 | 1h | ⬜ To-Do | Build /teacher/tests/[testId]/analytics. Avg score, score distribution bar chart, per-question accuracy (which questions most students got wrong → teacher knows what to re-teach). Student attempt list with scores. |
| F8.14 | Tests E2E test | 🧪 Test | 🟡 P1 | 1h | ⬜ To-Do | Test: create test with questions → student starts (check questions returned, no answers) → submit answers → check score calculation (correct +1, wrong -0.25) → check leaderboard rank → check FREE limit (3rd attempt blocked) → check auto-submit on timer end. |

FEATURE 9 Payments & Subscriptions (Razorpay) Freemium → Paid. Razorpay integration: UPI/cards/EMI. Webhook for auto-renew. Receipt via email+WhatsApp. Promo codes.

| # | Task / Sub-task | Layer | Pri | Time | Status | Detail / AI Prompt Hint |
| --- | --- | --- | --- | --- | --- | --- |
| F9.1 | Prisma Subscription + PromoCode models | 🗄 Database | 🔴 P0 | 30m | ⬜ To-Do | Subscription(student_id,plan_type,amount_paise,razorpay_order_id unique,razorpay_payment_id?,promo_code_used?,discount_paise,started_at,expires_at,is_active,auto_renew). PromoCode(code unique,discount_type,discount_value,max_uses,used_count,expires_at,is_active). Run migration. |
| F9.2 | Razorpay SDK setup + order creation | ⚙ Backend | 🔴 P0 | 1h | ⬜ To-Do | npm install razorpay. POST /api/v1/payments/create-order. Validate plan type. Apply promo code if provided (check validity, usage limit). Calculate final amount. razorpay.orders.create({amount, currency:'INR', receipt}). Return {order_id, amount, key_id}. |
| F9.3 | Razorpay frontend checkout integration | 🖥 Frontend | 🔴 P0 | 1h | ⬜ To-Do | Load Razorpay checkout script. On 'Pay Now' click: create order (API) → open Razorpay modal with {key, amount, order_id, name:'Krishna Academy', description, prefill:{contact:phone}}. On payment success: call POST /api/v1/payments/verify. |
| F9.4 | POST /api/v1/payments/verify — signature check | ⚙ Backend | 🔴 P0 | 1h | ⬜ To-Do | Verify HMAC: crypto.createHmac('sha256', KEY_SECRET).update(order_id+'¦'+payment_id).digest('hex') must equal razorpay_signature. On match: create Subscription record. Update User.plan + plan_expires_at. Increment promo_code.used_count. Return {success:true}. |
| F9.5 | POST /api/v1/payments/webhook — Razorpay events | ⚙ Backend | 🔴 P0 | 2h | ⬜ To-Do | Validate webhook signature. Handle events: payment.captured → same as verify flow. subscription.charged → auto-renew. payment.failed → send WhatsApp alert to student. refund.created → update Subscription.is_active=false. Idempotency check with razorpay_payment_id. |
| F9.6 | Payment receipt — email + WhatsApp | ⚙ Backend | 🔴 P0 | 1h | ⬜ To-Do | After successful payment: send Resend email with receipt template (plan, amount, valid until, invoice number). Send WhatsApp message: 'Payment successful! Rs.{amount} received. Plan active until {date}. Receipt: {link}'. Generate simple receipt PDF via @react-pdf/renderer. |
| F9.7 | Paywall modal UI | 🖥 Frontend | 🔴 P0 | 2h | ⬜ To-Do | Build PaywallModal component (shown when FREE limit hit). 3 plan cards: Monthly(Rs.149), Annual(Rs.999 — 'Best Value' badge), Batch Pack(Rs.299-499). Annual card has blue border highlight. Promo code input field. Payment method icons (UPI/Cards/EMI). 'Secure payment via Razorpay' trust badge. |
| F9.8 | Freemium gate middleware | ⚙ Backend | 🔴 P0 | 1h | ⬜ To-Do | Create checkPlanGate(userId, feature) utility. Feature gates: live_class (FREE: count this month >=3 → UPGRADE), video_stream (is_free=false → UPGRADE), notes_download (FREE → UPGRADE), test (FREE: count this week >=2 → UPGRADE). Called in respective API routes. |
| F9.9 | Subscription status page + cancel flow | 🖥 Frontend | 🔴 P0 | 1h | ⬜ To-Do | Build /profile/subscription page. Show: current plan, expiry date, auto-renew toggle. 'Cancel Auto-Renew' button with confirm dialog. On cancel: PUT /api/v1/payments/subscription/cancel → set auto_renew=false (plan stays active until expiry). |
| F9.10 | Admin promo code management | 🖥+⚙ Full Stack | 🟡 P1 | 1h | ⬜ To-Do | Admin creates promo codes: /admin/promo-codes. Form: code, discount type (% or flat), value, max uses, expiry. Table shows codes with used_count/max_uses. Toggle active/inactive. GET /api/v1/admin/promo-codes/:code validates code at checkout. |
| F9.11 | Subscription expiry reminder cron | ⚙ Backend | 🟡 P1 | 1h | ⬜ To-Do | Cron runs daily. Query Subscription where expires_at IN (now+3days) AND is_active=true AND auto_renew=false. Send WhatsApp+push: 'Tera plan 3 din mein expire hoga! Renew karo.' Also query expires_at IN (now+1day) → final reminder. |
| F9.12 | Admin revenue dashboard API | ⚙ Backend | 🟡 P1 | 1h | ⬜ To-Do | GET /api/v1/admin/revenue (admin only). Return: { mrr: sum of active monthly subs, arr: sum of annual subs, total_paid_users, plan_breakdown:{monthly,annual,batch}, monthly_revenue_last_6:[{month, amount}], churn_rate: cancelled this month / active last month * 100 }. |
| F9.13 | Payments E2E test | 🧪 Test | 🔴 P0 | 1h | ⬜ To-Do | Test: create Razorpay order → verify with correct signature → check Subscription created → check User.plan updated → check receipt email sent → hit live class after limit → get 403 UPGRADE_REQUIRED → pay → plan unlocked → rejoin → success. Test webhook payment.failed flow. |

FEATURE 10 Admin & Teacher Dashboards Admin: revenue, users, reports, broadcast notifications. Teacher: student analytics, course stats, class schedule.

| # | Task / Sub-task | Layer | Pri | Time | Status | Detail / AI Prompt Hint |
| --- | --- | --- | --- | --- | --- | --- |
| F10.1 | Admin dashboard — revenue metrics API | ⚙ Backend | 🟡 P1 | 1h | ⬜ To-Do | GET /api/v1/admin/revenue. MRR, ARR, total paid users, plan distribution, monthly revenue trend (last 6 months array), churn rate, new signups this week. Use Prisma aggregate queries. |
| F10.2 | Admin dashboard UI — web only | 🖥 Frontend | 🟡 P1 | 2h | ⬜ To-Do | Build /admin/dashboard. KPI cards row: MRR, ARR, Paid Users, Churn Rate. Revenue trend line chart (Recharts). Recent payments table. Quick actions: Send broadcast, Create promo, Export report. |
| F10.3 | Admin user management UI + API | 🖥+⚙ Full Stack | 🟡 P1 | 2h | ⬜ To-Do | GET /api/v1/admin/users?role=STUDENT&plan=FREE&search=riya. Table: name, phone, role, plan, last_active, joined_at. Actions: view profile, ban/unban (PUT .../ban), change plan. Pagination + CSV export. |
| F10.4 | Admin broadcast notification | 🖥+⚙ Full Stack | 🟡 P1 | 1h | ⬜ To-Do | POST /api/v1/admin/notifications/broadcast. Body: {channel: 'push'¦'whatsapp'¦'both', segment: 'all'¦'paid'¦'free'¦'class_10', title, message}. For push: loop FCM tokens in batches of 500. For WhatsApp: loop phone numbers. Return sent_count. |
| F10.5 | Teacher dashboard — stats API | ⚙ Backend | 🟡 P1 | 1h | ⬜ To-Do | GET /api/v1/teacher/dashboard (teacher role). Return: total_students (enrolled in teacher's courses), avg_attendance_pct, pending_homework_reviews, avg_rating, weekly_attendance_data:[{day, count}], recent_activity:[{student, action, time}]. |
| F10.6 | Teacher dashboard UI | 🖥 Frontend | 🟡 P1 | 2h | ⬜ To-Do | Build /teacher/dashboard. Sidebar nav. KPI cards: students, attendance %, pending reviews, rating. Attendance bar chart (last 7 days, Recharts). Recent student activity list. Quick action buttons: Schedule Live, Create HW, Upload Notes, Create Test. |
| F10.7 | Teacher student analytics page | 🖥+⚙ Full Stack | 🟡 P1 | 2h | ⬜ To-Do | Build /teacher/students. Table: student name, enrolled courses, avg test score, homework completion %, attendance %. Click student → detail view: per-subject progress, test history chart, homework submissions timeline. Search + filter by batch. |
| F10.8 | Teacher course analytics | 🖥+⚙ Full Stack | 🟡 P1 | 1h | ⬜ To-Do | GET /api/v1/teacher/courses/:id/analytics. Return: total_enrolled, completion_rate, avg_progress_pct, dropout_video (video with highest stop rate), most_watched_video, avg_watch_time. Show as charts in /teacher/courses/[id]/analytics. |
| F10.9 | Admin attendance report export | 🖥+⚙ Full Stack | 🟡 P1 | 1h | ⬜ To-Do | GET /api/v1/admin/reports/attendance?month=2026-04&format=pdf¦csv. CSV: all students × all classes matrix. PDF: formatted table with summary. Use papaparse for CSV. Use @react-pdf/renderer for PDF. Trigger download in admin UI. |
| F10.10 | Notification history log | 🗄 Database | 🟢 P2 | 30m | ⬜ To-Do | Create Notification model(user_id,type,channel,title,message,sent_at,is_read). Log all notifications sent. GET /api/v1/notifications/me returns unread count + list for in-app notification center. PUT /api/v1/notifications/read-all marks all as read. |
| F10.11 | In-app notification center UI | 🖥 Frontend | 🟡 P1 | 1h | ⬜ To-Do | Bell icon in navbar with unread badge count (Supabase Realtime subscription for live updates). Click → dropdown or slide panel showing notifications: icon, title, message, time, read/unread state. 'Mark all read' button. Infinite scroll for history. |
| F10.12 | Admin + Teacher dashboard E2E test | 🧪 Test | 🟡 P1 | 1h | ⬜ To-Do | Test: admin revenue API returns correct MRR. User ban → banned user gets 403 on next request. Broadcast sent to correct segment. Teacher dashboard stats match DB. Student analytics show correct avg. Attendance report CSV has correct data. |

# Sprint Plan — 6 Weeks to Launch

How to use this sprint plan Har sprint = 1 week. P0 features pehle — in 4 weeks sab P0 tasks complete. Week 5-6: testing + polish. Har task ek separate AI conversation = ek commit. Ek din mein 2-4 tasks complete karo.

| Sprint | Week | Focus | Features | Tasks | Est. Hours |
| --- | --- | --- | --- | --- | --- |
| Sprint 1 | Week 1 | Foundation Setup | F1 (Auth) + F2 (Courses) + DB Setup | ~26 tasks | ~32 hrs |
| Sprint 2 | Week 2 | Core Learning | F3 (Video Player) + F7 (Notes/PDF) | ~22 tasks | ~24 hrs |
| Sprint 3 | Week 3 | Live Classes | F4 (Live/Agora) + F6 (Attendance) | ~24 tasks | ~30 hrs |
| Sprint 4 | Week 4 | Student Features | F5 (Homework) + F9 (Payments/Razorpay) | ~25 tasks | ~30 hrs |
| Sprint 5 | Week 5 | Phase 2 Features | F8 (Tests/Quizzes) + F10 (Dashboards) | ~26 tasks | ~32 hrs |
| Sprint 6 | Week 6 | Polish & Launch | E2E Testing + Bug Fixes + Deploy + App Build | All tests | ~20 hrs |

## Daily AI Workflow — How to use this document

| Step | Action | Example |
| --- | --- | --- |
| 1 | Open this document, pick 1 task (To-Do + P0 first) | Today I will do: F1.3 — MSG91 OTP send API |
| 2 | Open Cursor / Claude / v0 | Start new conversation |
| 3 | Give AI the context from Document #1 + #2 | Paste the one-line prompt from PRD Doc #1 summary page |
| 4 | Give AI the specific task from Detail column | POST /api/v1/auth/otp/send. Validate phone... (from F1.3) |
| 5 | Review AI output, test it, commit to git | git commit -m 'feat: F1.3 OTP send endpoint with MSG91' |
| 6 | Update Status column to ✅ Done | Mark F1.3 as Done in this document |
| 7 | Repeat for next task | Next: F1.4 — OTP hash storage in Redis |

Document #4 — Feature Breakdown  |  Krishna Academy Upleta  |  v1.0  |  April 2026  |  Prepared by Tushar